## Slide 1
MW Program
Construction update
09/29/2026
Viaero Wireless · Nokia Program Team
Nokia internal use

## Slide 2
Agenda for 09/29/2026 meeting
09/29/2026
Nokia internal use
01
Material and NTP Status
02
Cx Start and Cx Complete Status
03
MSS Readiness
04
HOPs in Progress
05
CX Start look ahead
06
September POR
07
October POR
09
09
Decom Review
09
10
SCOP Review
09
11
Action Items Log
09
08
November POR

## Slide 3
What Changed Dashboard
Compared to 9/15/2026 · 09/22/2026
09/22/2026
Nokia internal use
184
Total Starts
+4 vs 09/22/2026
173
Completions
+5 vs 09/22/2026
11
HOPs in Progress
-1 vs 09/22/2026
200
NTPs Issued
+1 vs 09/22/2026
★ Construction Completed: 173 of 242 HOPs (71%) – 69 HOPs Remaining
NTP Start Changes by Month
September POR: 24 of 25 HOPs with NTP
November POR: 5 of 20 Hops with NTPs
October POR: 10 of 25 Hops with NTPs
★ 233 HOPs assigned to Nokia – Red Flag 9/21/2026, Terry provided addition 9 pending red flag. Total 242
242
Nokia Assigned Hops
+ 9 Pending Red Flag

## Slide 4
Cx Start Status
Month-over-month · Forecast = MS15 Implementation Start F
09/29/2026
Nokia internal use
Cx Starts
Chart: 
| Jan/26+ | 26-Feb | 26-Mar | 26-Apr | 26-May | 26-Jun | 26-Jul | 26-Aug | 26-Sep | 26-Oct | 26-Nov | 26-Dec | 27-Jan | 27-Feb | 27-Mar
Plan | 24 | 7 | 18 | 23 | 22 | 26 | 28 | 13 | 28 | 20 | 20 | 10 | 8
Forecast | 24 | 7 | 18 | 23 | 22 | 26 | 28 | 13 | 25 | 5 | 4
Actual | 24 | 7 | 18 | 23 | 22 | 26 | 28 | 13 | 23
Monthly construction start activity for qualified HOPs with NTP issued and materials received.​
Sept. – 25 F Starts, 25 qualified, 23 started
Nebraska only – 5 Starts remaining
    3 have NTP
    2 pending NTP and/or blockers.
    All starting on or before 10/5.

## Slide 5
Cx Complete Status
Month-over-month · Completions = MS16 Implementation Ends F
09/22/2026
Nokia internal use
Cx Completes
Chart: 
| Jan/26+ | 26-Feb | 26-Mar | 26-Apr | 26-May | 26-Jun | 26-Jul | 26-Aug | 26-Sep | 26-Oct | 26-Nov | 26-Dec | 27-Jan | 27-Feb | 27-Mar
Plan | 13 | 7 | 8 | 14 | 29 | 31 | 30 | 19 | 28 | 22 | 20 | 15 | 10 | 4
Forecast | 13 | 7 | 8 | 14 | 29 | 31 | 30 | 19 | 25 | 12 | 4
Actual | 13 | 7 | 8 | 14 | 29 | 31 | 30 | 19 | 21
Monthly construction start activity for qualified HOPs with NTP issued and materials received.​
Sept. – 25 F Completed, 25 qualified
Nebraska only – 11 completions remaining
    6 are in progress
    5 remaining to start; all expected to start on or before 10/05, and complete before 10/15.

## Slide 6
MSS Readiness, Power Needed
4 started (last 7 days) · 8 forecast (next 7 days)
09/29/2026
Nokia internal use
Sites Started — MSS Ready or Ready Soon (4)
HOP | Viaero Ops Mgr | Status | Cx Start | CX Notes / Live Status
NE-GI_UNION_PACIFIC-NE-GI_INDUSTRIAL_PARK | C. Bolton | Ready | 09/23/2026 | 
CO-ALAMOSA-CO-ALAMOSA_HOSP | S. Jordan | Ready | 09/25/2026 | 
NE-LEXINGTON_TG-NE-LEXINGTON | C. Bolton | Ready | 09/25/2026 | 
CO-PRITCHETT_NORTH-CO-NINE_MILE | S. Jordan | Ready | 09/25/2026 | 9/29: Completed

## Slide 7
Construction Start Look ahead
8 starts in the 7-day look-ahead · 09/29/2026 – 09/29/2026
09/29/2026
Nokia internal use
8 starts in the 7-day look-ahead
HOP | NTP | Fc Start | Site CM | Viaero Ops | NTP Waiting On | Comments
CO-HOOPER-CO-CENTER | ✓ | 09/30/2026 | Steve | S. Jordan | NTP Complete | 
NE-GI_INDUSTRIAL_PARK-NE-GILTNER | ✓ | 09/30/2026 | Chris | C. Bolton | NTP Complete | 
NE-ALLIANCE_HOSP-NE-ALLIANCE | ✓ | 10/01/2026 | Steve | B. Brumbaugh | Hosp pending LL approval | 
NE-LEXINGTON_DT-NE-LEXINGTON_NORTH | ✗ | 10/02/2026 | Chris | C. Bolton | NTP | 
NE-BROKEN_BOW_NW-NE-BROKEN_BOW | ✓ | 10/02/2026 | Tom | C. Bolton | NTP Complete | 
CO-BLANCA_WEST-CO-ALAMOSA | ✓ | 10/05/2026 | Chris | S. Jordan | NTP Complete | 
NE-CEDAR_BLUFF-KS-OBERLIN | ✓ | 10/05/2026 | George | C. Bolton | NTP Complete | 
CO-MANZANOLA_DT-CO-MANZANOLA | ✗ | 10/06/2026 | Steve | S. Jordan | pending LLD approval | 

## Slide 8
Hops in Progress
11 HOPs started · Green=On Track · Yellow=At Risk · Red=Escalation · ⚑=Needs Attention
09/29/2026
Nokia internal use
HOP | Cx Start | Fc End | Risk | Comments / Live Status
NE-BURWELL_DT_HUB-NE-BURWELL | 09/01 | 09/29/26 |  | 9/28/2026: (CJ) Couldnt get on the site until today due to the event over weekend. Crew will be on site today and compl
NE-KEARNEY_MALL-NE-KEARNEY_CAMPUS | 09/15 | 09/30/26 |  | 9/28/2026: (CJ) Waiting on Chris B to let us know if we can move forward. ¦ 9/23/2026: (CJ) Talked with SS, the got in t
NE-MERRITT_RESERVOIR-NE-VALENTINE_SOUTH | 09/17 | 09/30/26 |  | 9/28/2026: (CJ) Meeting Chris B this morning at 10 at Valentine south. Tracking for HOT cut. ¦ 9/24/2026: (CJ) Valentine S
CO-PUEBLO_BYPASS-CO-ABBEY | 09/18 | 09/30/26 |  | 9/23/2026:(CJ) after 2 previous HOPS GC will complete this one by end of month.
CO-ALAMOSA-CO-ALAMOSA_SALES | 09/16 | 10/01/26 |  | 9/28/2026; (CJ) If weather holds we will be able completed. ¦ 9/24/2026: (CJ) On track ¦ 9/23/2026:(CJ) Weather not looking
★ NE-GI_UNION_PACIFIC-NE-GI_INDUSTRIAL_PARK | 09/23 | 10/02/26 |  | 9/23/2026: (CJ) Working on the industrial side of this HOP. SS is on the Union specific. They working it as well and nee
NE-GI_INDUSTRIAL_PARK-NE-GIBBON | 09/14 | 10/03/26 |  | 9/28/2026: (CJ) Material picked up on Saturday and tracking 10/3. ¦ 9/24/2026: (CJ) Material expect in by 9/25. at the co
CO-STERLING_DT-CO-STERLING_FG | 09/17 | 10/05/26 |  | 9/24/2026: (CJ) Crew has Sterling DT prepped and ready to go waiting on Samsung ¦ 9/17: start on DT side today, will do sh
★ NE-LEXINGTON_TG-NE-LEXINGTON | 09/25 | 10/05/26 |  | 9/28/2026: (CJ) Tower MOD is still in progress on the Lexington TG. Crew working on the Lexington side and punch lists .
★ CO-PRITCHETT_NORTH-CO-NINE_MILE | 09/25 | 10/05/26 |  | 9/23/2026: (CJ) Material being picked up today from warehouse and ITW if approved. ¦ 9/21/2026:(CJ) Scheduled to pick up t
★ CO-ALAMOSA-CO-ALAMOSA_HOSP | 09/25 | 10/07/26 |  | 9/28/2026: (CJ) Worked the Alamosa side while we wait on the Hosp. Approval. ¦ 9/17: pending feedback from Kyle, green lig

## Slide 9
New Starts & Completions Since Last Meeting
HOPs that started or completed construction since the last build
09/29/2026
Nokia internal use
HOP | GC | CM
HOP | GC | CM
New Starts
Completions

## Slide 10
25 Forecasted September POR
September Plan of Record
09/29/2026
Nokia internal use
25
September POR HOPs
24
With NTP
1
Pending NTP
September POR
24
Green - High Confidence
1
Yellow - Medium Risk
0
Red - High Risk
24 with NTP of 25 POR · 1 pending NTP

## Slide 11
24 with NTP of 25 POR
September POR with NTPs
09/29/2026
Nokia internal use
HOP | Mat | NTP | Start | End | NTP Action Owner | NTP Status / Notes
NE-BURWELL_DT_HUB-NE-BURWELL | ✓ | ✓ | 09/01 | 09/29 |  | NTP Complete
NE-GERING_DT-NE-GERING_NORTH | ✓ | ✓ | 09/02 | 09/03 |  | NTP Complete
NE-HOBIN-NE-SWAN_LAKE_NORTH | ✓ | ✓ | 09/02 | 09/18 |  | NTP Complete
CO-ANTONITO_DT-CO-ANTONITO | ✓ | ✓ | 09/03 | 09/23 |  | NTP Complete
NE-ONEILL-NE-MIDWAY | ✗ | ✓ | 09/04 | 09/20 |  | NTP Complete
CO-ROMEO_DT-CO-MANASSA_NW | ✓ | ✓ | 09/05 | 09/25 |  | NTP Complete
NE-JOHNSTOWN-NE-VALENTINE_SOUTH | ✓ | ✓ | 09/05 | 09/19 |  | NTP complete. New tower complete
CO-MONTE_VISTA-CO-ALAMOSA_SALES | ✓ | ✓ | 09/09 | 09/12 | Nokia | NTP Complete
NE-KEARNEY_ALLTELL-NE-KEARNEY_CAMPUS | ✓ | ✓ | 09/14 | 09/17 |  | NTP Complete
NE-HASTINGS_NORTH-NE-HASTINGS_NAPA | ✓ | ✓ | 09/14 | 09/16 |  | NTP Complete
NE-GI_INDUSTRIAL_PARK-NE-GIBBON | ✓ | ✓ | 09/14 | 10/03 |  | NTP Complete
NE-COLUMBUS_SW-NE-COLUMBUS_DT | ✓ | ✓ | 09/15 | 09/23 |  | NTP complete
NE-STAPLETON-NE-THEDFORD_SOUTH | ✓ | ✓ | 09/15 | 09/25 |  | NTP complete
NE-LEXINGTON_HS-NE-LEXINGTON | ✓ | ✓ | 09/16 | 09/17 |  | NTP Complete
CO-ALAMOSA-CO-ALAMOSA_SALES | ✓ | ✓ | 09/16 | 10/01 |  | NTP Complete
NE-MERRITT_RESERVOIR-NE-VALENTINE_SOUTH | ✓ | ✓ | 09/17 | 09/30 |  | NTP Complete
NE-KEARNEY_MALL-NE-KEARNEY_CAMPUS | ✓ | ✓ | 09/18 | 09/30 |  | NTP Complete
CO-PUEBLO_BYPASS-CO-ABBEY | ✓ | ✓ | 09/18 | 09/30 | No Action | NTP Complete
NE-GI_UNION_PACIFIC-NE-GI_INDUSTRIAL_PARK | ✓ | ✓ | 09/23 | 10/02 |  | SBA stacking tower now - ready 9/14/26
CO-ALAMOSA-CO-ALAMOSA_HOSP | ✓ | ✓ | 09/24 | 10/07 | ITW | NTP Complete. Hosp Pending LL approval
NE-LEXINGTON_TG-NE-LEXINGTON | ✓ | ✓ | 09/25 | 10/05 |  | NTP Complete
CO-PRITCHETT_NORTH-CO-NINE_MILE | ✓ | ✓ | 09/25 | 10/05 |  | NTP Complete
CO-HOOPER-CO-CENTER | ✓ | ✓ | 09/30 | 10/10 |  | NTP Complete
NE-GI_INDUSTRIAL_PARK-NE-GILTNER | ✗ | ✓ | 09/30 | 10/10 |  | NTP Complete

## Slide 12
1 of 25 pending NTP
September POR Pending NTPs
09/29/2026
Nokia internal use
External Blockers (1) — ITW · Samsung · Viaero
HOP | Start | End | Action Owner | NTP Blocker / Waiting On | Comments
CO-STERLING_DT-CO-STERLING_FG | 09/17 | 10/05 | Samsung/ITW | FG: Samsung Combo CDs rejected 9/2, then ITW | 9/22/2026: Received the CDs from SS on 9/14 and submitt

## Slide 13
25 Forecasted October POR
October Plan of Record
09/29/2026
Nokia internal use
25
October POR HOPs
10
With NTP
15
Pending NTP
October POR
10
Green - High Confidence
4
Yellow - Medium Risk
11
Red - High Risk
10 with NTP of 25 POR · 15 pending NTP

## Slide 14
10 with NTP of 25 POR
October POR with NTPs
09/29/2026
Nokia internal use
HOP | Mat | NTP | Start | End | NTP Action Owner | NTP Status / Notes
NE-ALLIANCE_HOSP-NE-ALLIANCE | ✓ | ✓ | 10/01 | 10/11 | ITW | Hosp pending LL approval
NE-BROKEN_BOW_NW-NE-BROKEN_BOW | ✓ | ✓ | 10/02 | 10/12 |  | NTP Complete
CO-BLANCA_WEST-CO-ALAMOSA | ✗ | ✓ | 10/05 | 10/15 |  | NTP Complete
NE-CEDAR_BLUFF-KS-OBERLIN | ✗ | ✓ | 10/05 | 10/15 |  | NTP Complete
CO-MANZANOLA-CO-FOWLER | ✗ | ✓ | 10/08 | 10/18 |  | NTP Complete
CO-MOFFAT-CO-HOOPER | ✓ | ✓ | 10/10 | 10/20 |  | NTP Complete
CO-CENTER-CO-SAGUACHE | ✓ | ✓ | 10/11 | 10/21 |  | NTP Complete
CO-RUSH-CO-FOWLER_NORTH | ✗ | ✓ | 10/16 | 10/26 |  | NTP Complete
CO-SANFORD-CO-LA_JARA | ✓ | ✓ | 10/22 | 10/30 |  | NTP Complete
CO-MANZANOLA-CO-ROCKY_FORD | ✗ | ✓ | 10/24 | 11/03 |  | NTP Complete

## Slide 15
15 of 25 pending NTP
October POR Pending NTPs
09/29/2026
Nokia internal use
External Blockers (11) — ITW · Samsung · Viaero
HOP | Start | End | Action Owner | NTP Blocker / Waiting On | Comments
NE-LEXINGTON_DT-NE-LEXINGTON_NORTH | 10/02 | 10/12 | Viaero | NTP | 9/22/2026: Approved by Wes.
CO-MANZANOLA_DT-CO-MANZANOLA | 10/06 | 10/16 | Viaero | pending LLD approval | 
WY-TORRINGTON_SOUTH-WY-TORRINGTON_DT | 10/08 | 10/18 | ITW | DT - pending Vertical Bridge approval | 9/22/2026: Still in review with VB. ¦ 9/8/2026: Still pe
CO-HUGHES-CO-KIRK | 10/10 | 10/20 | Viaero | Pending service assignment | 
KS-GREAT_BEND_CENTRAL-KS-ELLINWOOD | 10/11 | 10/21 | Nokia & Viaero | Pending LLD approval. | 
KS-ATWOOD-KS-MIDWAY_KS | 10/15 | 10/25 | Nokia & Viaero | Pending LLD approval. | 
KS-MIDWAY_KS-KS-OBERLIN | 10/15 | 10/25 | Nokia & Viaero | Pending LLD approval. | 
KS-PHILLIPSBURG-KS-WALNUT | 10/18 | 10/28 | Nokia & Viaero | Pending LLD approval. | 
KS-PRAIRIE_VIEW-KS-PHILLIPSBURG | 10/21 | 10/31 | Nokia & Viaero | Pending LLD approval. | 
CO-GRANGER-CO-HANNA | 10/26 | 11/05 | Viaero | 0 | 
CO-CROOK-CO-SEDGWICK | 10/26 | 11/05 | Viaero | Pending service assignment | 
Program Team Actions (4)
HOP | Start | End | Action Owner | NTP Blocker / Waiting On | Comments
CO-TOBE_SW-CO-TREMENTINA | 10/21 | 10/31 | Nokia | pending LLD submittal | 
KS-HAYS_EAST-KS-HAYS_NW | 10/21 | 10/31 | Nokia | pending LLD submittal. | 
KS-BUNKER_HILL-KS-DORRANCE | 10/25 | 11/04 | Nokia | pending LLD submittal. | 
KS-GOODLAND-KS-BREWSTER | 10/29 | 11/08 | Nokia | pending WP & LLD submittal. Pending ITW reso | 

## Slide 16
20 Forecasted November POR
November Plan of Record
09/29/2026
Nokia internal use
20
November POR HOPs
5
With NTP
15
Pending NTP
November POR
5
Green - High Confidence
6
Yellow - Medium Risk
9
Red - High Risk
5 with NTP of 20 POR · 15 pending NTP

## Slide 17
5 with NTP of 20 POR
November POR with NTPs
09/29/2026
Nokia internal use
HOP | Mat | NTP | Start | End | NTP Action Owner | NTP Status / Notes
CO-MONTE_VISTA-CO-CENTER | ✓ | ✓ | 11/01 | 11/11 |  | NTP Complete
CO-TOWNER_DT-CO-TOWNER | ✓ | ✓ | 11/05 | 11/15 |  | NTP Complete
CO-ABBEY-CO-HOGBACK | ✓ | ✓ | 11/09 | 11/17 |  | NTP Complete
CO-DEL_NORTE-CO-MONTE_VISTA | ✗ | ✓ | 11/16 | 11/26 |  | NTP Complete
CO-DEL_NORTE-CO-HANNA | ✓ | ✓ | 11/16 | 11/26 |  | NTP Complete

## Slide 18
15 of 20 pending NTP
November POR Pending NTPs
09/29/2026
Nokia internal use
External Blockers (9) — ITW · Samsung · Viaero
HOP | Start | End | Action Owner | NTP Blocker / Waiting On | Comments
CO-FARISITA-CO-STRONG | 11/01 | 11/11 | Viaero | Pending service quote submittal | 
CO-MONTE_VISTA_COOP-CO-MONTE_VISTA | 11/01 | 11/11 | Viaero | pending LLD approval. | 
CO-ALAMOSA_SW-CO-ALAMOSA_SALES | 11/01 | 11/11 | Viaero | Ready for NTP | 9/22/2026: Dalla will issue.
CO-PROSPECT_EAST-CO-HOYT_NORTH | 11/03 | 11/13 | Viaero | pending WP approval & LLD approval on one sit | 7/8: per Don's email, P4G3 – Site moved
KS-CLAFLIN-KS-HOLYROOD | 11/04 | 11/14 | Nokia & ITW | pending LLD submittal. Pending ITW resolutio | 
KS-GOODLAND-KS-GOODLAND_DT_NORTH | 11/06 | 11/16 | Nokia & Viaero | Pending LLD approval. | 
KS-WAKEENEY-KS-QUINTER | 11/10 | 11/18 | Viaero | Pending NTP | 
KS-WAKEENEY-KS-ELLIS_NORTH | 11/18 | 11/26 | Viaero | Pending NTP | 
CO-CENTER_NORTH-CO-CENTER | 11/21 | 11/30 | Viaero | Ready for NTP | 9/22/2026: Dallas will issue.
Program Team Actions (6)
HOP | Start | End | Action Owner | NTP Blocker / Waiting On | Comments
CO-FM_OFFICE-CO-FM_HOSP | 11/08 | 11/18 |  |  | 
CO-FARISITA-CO-GARDNER | 11/11 | 11/21 | Nokia | pending LLD submittal | 7/3: PRIORITIZE- both sites are mountain sites with dif
CO-JULESBURG_COURTHOUSE-CO-JULESBURG_DT | 11/14 | 11/24 | Nokia | pending LLD submittal. | 6/16: cxld per 6/12 red flag report
CO-MONTE_VISTA_EAST-CO-MONTE_VISTA | 11/16 | 11/26 | Nokia | Pending NTP | 7/23: Ethos doing RAN for SS at East
KS-GRAINFIELD-KS-QUINTER | 11/18 | 11/26 | Nokia | pending WP & LLD submittal. | 
CO-MONTE_VISTA_SW-CO-MONTE_VISTA | 11/21 | 11/30 | Nokia | Pending NTP | 

## Slide 19
Action Items Log
Nokia internal use
Action Item | Status | Owner
Add Scop Slide | Completed | Nokia
From Terry - ¦¦Los ochos to Jigante MW¦¦ I’d like to put this as an action item on the weekly CX call. This is a link that was not captured in the FCC application, but we have validated that there is Huawei MW here. We will need to replace it however it goes to a private residence, thus Viaero will do the installation. However we need to get this stuff on order. It is also a site in the mountains down by Gunnison so is one we wanted before winter. – 9/22: PCNs sent to Wes. | Completed | Nokia
From Chris B. Lexington DT to Lexington N – MW Hop Equipment Status (9/8- Nokia- HOP Cancelled then pulled back in. Working on equipment reallocations) – 9/22 Temp solution equipment expected Oct. 9th. 9/29 : pulled in to today in Sidney. Ainsworth to Ainsworth S – AIM issue – (9/8- Nokia Call scheduled to review concerns today) 9/22: Aims are shipping to the LSC today and expected no later then Friday. Shipping to Sydney - 9/23: Delivered being brought up to Sidney by scot today. Allwave should be able to pick up by tomorrow. CoreEVO card replacement. – (Eusitis to Elwood, Ryan working on the process and scheduling call with Viaero and going through the process to get this taken care of through cares) 9/22: Follow-up convo internal to make sure we have the correct person to present the process for the care tickets. – 9/29 : confirming with Ryan on the kickoff on the cares this week 9/30. | In progress 2 of 3 completed | Nokia

## Slide 20
Thank You
End of Presentation
09/29/2026
Viaero Wireless · Nokia Program Team · Questions Welcome
Nokia internal use